## Sheet1
CHILD(REN): ****
PRE-PROCEEDINGS TIMELINE OVERVIEW - CALCULATED TO MAXIMUM 16 WEEKS (SEE PRE-PROCEEDINGS TIMELINE AUGUST 2021 FOR MORE DETAIL)
WEEK COMMENCING | WEEK | MEETINGS | CSC ACTIONS | PARENTING & SIBLING ASSESSMENTS | ASSESSMENTS OF FAMILY & FRIENDS | LEGAL ACTIONS | WEEK
| -3 |  | Fully completed and approved (by TM & HoS) Initial LPM Request and supporting documents to Legal |  |  |  | -3
| -2 | Initial LPM (HoS, TM, SW, Legal & Minute-Taker) - Outcome to enter pre-proceedings process | Referral to Care & Resource Panel |  |  |  | -2
| -1 |  | Draft Pre-Proceedings Meeting (PPM) letter and Parenting Assessment Plan - send to Legal for comment/amendment | Draft Parenting Assessment Plan w/c dates and details of sessions |  | Comment/amend PPM letter and Parenting Assessment Plan | -1
|  |  | Agreed PPM letter and Parenting Assessment Plan hand delivered to parent with list of solicitors, parent pack and s20 leaflet (if required) |  |  | Draft proposed PPM Agenda and send to TM (with finalised letter & PA Plan)
INSERT DATE | 0 | First PPM with primary carer (Parent & their Legal, SW, TM, Legal & Minute-Taker) |  | Finalise Parenting Assessment Plan with dates of sessions - copy to legal & parent to sign |  |  | 0
INSERT DATE | 1 |  | FGC / FNM referral (if not already taken place) | Parenting & Sibling Assessments (Social Worker / Agent Social Worker) | Initial Screenings (Social Worker) | Draft Pre-Proceedings Plan to capture agreements reached at PPM | 1
|  |  | Arrange signature of agreed Pre-Proceedings Plan & Consent Form if not already done, signed copies to Legal |  |  | Draft Consent Form for signature by parent, if not done at PPM
|  |  | Arrange signature of finalised Parenting Assessment Plan, signed copy to Legal |  |  | Lead on expert instructions, drug and/or alcohol tests, paternity tests, reports, disclosure, DNA tests.
Referrals for support/intervention as agreed at PPM
#VALUE! | 2 |  |  |  | Viability Assessments (Kinship Team & Social Worker) |  | 2
#VALUE! | 3 | [5 empty] | 3
#VALUE! | 4 |  |  |  | Full Assessments (Kinship Team) |  | 4
#VALUE! | 7 | Review LPM (HoS, SW, TM, Legal & Minute-Taker) Possible outcomes: - Issue care proceedings - Continue in pre-proceedings |  |  |  | Lead on obtaining any additional information/evidence required to inform future decision-making. If RPPM, provide TM with RPPM agenda & updated Pre-Proceedings Plan. | 7
#VALUE! | 8 | Depending on outcome of RLPM and if required: Social Care Review Meeting with parents - plan on track OR Review PPM (Parent & their Legal, SW, TM, Legal & Minute-Taker) to advise decision made to issue care proceedings (unusual to meet with parent if continuing in pre-proceedings) |  |  |  |  | 8
#VALUE! | 12 |  |  |  |  | Comment on Parenting (& Sibling) Assessment | 12
#VALUE! | 15 | Review LPM (HoS, SW, TM, Legal & Minute-Taker) Possible outcomes: - Issue care proceedings - Close pre-proceedings - Continue in pre-proceedings (with extension agreed) | Finalise any pre-proceedings tasks, eg draft updated Safety Plan etc |  |  | Finalise any pre-proceedings tasks, eg updating disclosure, circulate assessments prior to Review PPM, comment on updated Support Plan etc Provide TM with RPPM Agenda & updated Pre-Proceedings Plan. | 15
#VALUE! | 16 | Review Pre-Proceedings Meeting (Parent & their Legal, SW, TM, Legal & Minute-Taker) - to advise outcome of RLPM |  |  |  |  | 16
#VALUE! | End 16 | PRE-PROCEEDINGS END DATE |  |  |  |  | End 16